## Pool 1
Priority | Story Type | Story | Notes
1 | User | As a user I want to be able to perform a basic search by typing in a medicine name and see results
2 | User | As a user I want all searches to be equipped with auto populate
3 | User | As a user I would like to know if my drug has any report adverse events so that I can be more aware.
4 | User | As a user I would like to know the details of any adverse events report about my drug so that I can be more informed.
5 | User | As a user I would like to know if my drug has been recalled so that I can be more aware.
6 | User | As a user I would like to know the details of any recalls about my drug so that I can be more informed.
7 | User | As a user I would like to see other contextual information about my drug by pulling data from other sources so that I increase my awareness.
8 | User | As a user I would like to add dynamic iconography to my recall and event data that will will indicate recency.
9 | User | As a user I would like to filter my event results so that I can access reports that are pertinent to me
10 | User | As a user I would like to filter my recall results so that I can access reports that are pertinent to me
11 | User | As a user I would like to see for any searched drug the top 5 reactions so that I can be more aware of the drug's impact severity
12 | User | As a user I would like to see for any searched drug all of the outcomes gropued by # of events.
13 | User | As a researcher I would like to see my data visually displayed so that I can understand trending more readily.
14 | User | As a user I would like to see more pertinant details about my drug such as generic brand names, icon based warnings etc.
15 |  | As a user I would like to see a loading gif while waiting for my results to return
16 | User | As a user I would like to share data from med check to social media outlets such as twitter
17 | User | As a user I would like to email my search result to a friend to share knowledge
18 | User | As a user I would like to submit feedback comments about my search result to contribute to the overall reliability of the data
19 | User | As a user I would like to submit a confidence or usability rating about my search result to contribute to the overall reliability of the data
20 | Spike | Research other data sets within openFDA to broaden our data footprint to increase contextual awareness
21 | Spike | Research other data sets outside of openFDA about drugs to deepen our data footprint to increase contextual awareness
22 | Spike | Find data source where I can search fo ra drug info based on unique ID to link to other websites
| Technical | Need to create DNS names for environments
| Technical | Dedup data
| Technical | Service - Implement Call to Get Image
| Technical | Dashboard Data Identification
| Technical | Front End - Implment Auto Populate
| Technical | Display Drug Description data
| Technical | Display Side Effects data
| Technical | Display Recall data
| Technical | Display Adverse Effects data
| Technical | Sync UI with Application
| Technical | Service - Set up Backend Code
| Technical | Service - Set up Frontend Code
| Technical | Service - Set up API for recall
| Technical | Service - UI & Service for integration for recall
| Technical | Service - Set up API for adverse events
| Technical | Service - UI & Service for integration for adverse events
| Technical | Set skip limit to adverse event data to 5000
| Technical | Set skip limit to recall data to 5000
| Technical | Manage application messages and constants
| Technical | Set up SSL certificate
| Technical | Manage error handling
| Technical | Implement Events Filter API
| Technical | Implement services for reference data
| Technical | API for top 5 reactions
| Technical | API for all outcomes
| Technical | Refactor UI Code
| UX | Develop User Personas
| UX | Develop Workflows
| UX | Develop Competitive Analysis
| UX | Develop User Survey
| UX | Cardsorting
| UX | Conduct usability testing
| UX | Develop heuristic evaluation
| UX | Technical Spike - Reseach other data sets to increase contextual data footprint
| UX | Technical Spike - Further analyze FDA data set to determine holistic visualization
| UX | Develop new personas for new feature rollout
| UI | Create new iconography for recall and event line items
| UI | Come up with application name
| UI | Develop application logo
| UI | Develop application tagline
| UI | Develop color palette
| UI | Select Font
| UI | Develop imagery
| UI | Develop homepage search wireframe
| UI | Develop results wireframe
| UI | Develop details wireframe
| UI | Develop responsive HTML skeleton
| UI | Develop Global CSS
| UI | Research content for homepage
| UI | Modify dial icons
| UI | Modify color palette
| UI | Filter
| UI | Create infographs symptons layout
| UI | Recall adverse event icons
| UI | Imagery visualization
| UI | Create ledging for diagram
| UI | Update frontpage
| UX/UI | Review Data Sets
| UX/UI | Review Work Flow
| UX/UI | Review User Stories
| DevOps | Install Jenkins (integration server)
| DevOps | Install Java and set environment variables
| DevOps | Install tomcat and jenkins war file
| DevOps | Install nginx and configure reverse proxy
| DevOps | Create andInstall SSL Certificate for nginx
| DevOps | Create Jenkins job(s) - build, test, deploy and github hook
| DevOps | Create init.d job for Jenkins
| DevOps | Install MEAN Server (production server)
| DevOps | Install nvm, nodejs and forever
| DevOps | Install nginx and configure reverse proxy
| DevOps | Create init.d job for application
| DevOps | Infrastructure Automation (production server)
| DevOps | Packer creation of AMI
| DevOps | Packer creation of Vagrant box
| DevOps | Chef recipe for nginx
| DevOps | Chef recipe for nvm
| DevOps | Chef recipe for init.d
| DevOps | Infrastructure Testing
| DevOps | Chef Test forChef recipes
| DevOps | Install and configure nagios (monitoring) on integration server
| DevOps | Install static code analysis (???)
| DevOps | Ongoing Tasks
| DevOps | Support development team (mongodb database seeding, dev environment)
| DevOps | Update Jenkins
| DevOps | Install docker container for node.js
| DevOps | Install docker container for mongodb
| DevOps | Integrating the two containers
| DevOps | Docker Mongo container development
| DevOps | Docker Mean container development
| DevOps | Docker build scripts
| DevOps | Docker hub integration
| DevOps | Docker init.d scripts
| DevOps | Docker container integration